# VM Migration Summary

West US to West US 3 Migration Plan

Subscription: sub-corp-prod-001

# OVERVIEW

Tony, you requested moving VMs from West US to West US 3 in the sub-corp-prod-001 subscription. I have completed the initial assessment below.

# VMs FOUND IN WEST US

| VM Name | Resource Group | Type | Can Move Easily? |
| --- | --- | --- | --- |
| PyxSftp | PRODUCTION | SFTP Server | YES |
| vm-fileserver | PRODUCTION | File Server | YES |
| vm-pdc | PRODUCTION | Domain Controller | REQUIRES PLANNING |

# WHAT WE CAN MOVE (Low Risk)

| VM | Downtime Required | Method |
| --- | --- | --- |
| PyxSftp | 2-5 minutes | Azure Site Recovery |
| vm-fileserver | 2-5 minutes | Azure Site Recovery |

These VMs can be moved with minimal downtime using Azure Site Recovery (ASR). Data replicates while VMs are running, then we do a quick failover.

# WHAT REQUIRES SPECIAL PLANNING (High Risk)

| VM | Risk | Why |
| --- | --- | --- |
| vm-pdc | HIGH | This is a Domain Controller. Moving it incorrectly can break authentication for ALL users and servers. |

For vm-pdc (Domain Controller), we need to know:

- Is this the ONLY Domain Controller?

- Is there a secondary DC in another region?

- If it's the only DC, we should NOT move it until we have a backup DC

# INFORMATION NEEDED FROM YOU

Please provide the following so we can proceed:

| # | Question | Your Answer |
| --- | --- | --- |
| 1 | Is vm-pdc the only Domain Controller? Or is there a backup DC? |  |
| 2 | Do we have an existing Recovery Services Vault in West US 3? |  |
| 3 | What is the approved maintenance window? (Date/Time for downtime) |  |
| 4 | Are there any other VMs in West US that need to move? (I only found 3) |  |
| 5 | Do these VMs have static IP addresses that applications depend on? |  |
| 6 | Are there any load balancers or public IPs attached to these VMs? |  |
| 7 | What is the acceptable downtime? (Minutes or hours?) |  |
| 8 | Should we keep the old VMs as backup or delete them after migration? |  |

# WHAT WE NEED BEFORE MIGRATION

| Requirement | Status | Notes |
| --- | --- | --- |
| Recovery Services Vault in West US 3 | Need to confirm | Required for ASR replication |
| Virtual Network in West US 3 | Need to create | VMs need a network to connect to |
| Subnet configuration | Need to plan | Must match current setup |
| NSG (Network Security Groups) | Need to replicate | Firewall rules must match |
| Backup of all VMs | Need to create | Safety backup before migration |
| DNS updates planned | Need to plan | If IPs change, DNS must update |
| Secondary Domain Controller | Need to confirm | Required before moving vm-pdc |

# RECOMMENDED MIGRATION PLAN

## Phase 1: Preparation (1-2 days)

- Create Virtual Network in West US 3

- Create Recovery Services Vault

- Set up NSG rules

- Take full backups of all VMs

## Phase 2: Replication (2-3 days)

- Enable Azure Site Recovery

- Start replicating VMs (VMs stay running during this)

- Wait for initial sync to complete

## Phase 3: Test Failover (1 day)

- Do a TEST failover (doesn't affect production)

- Verify VMs work in West US 3

- Fix any issues found

## Phase 4: Production Failover (Maintenance Window)

- Schedule maintenance window

- Failover PyxSftp (2-5 min downtime)

- Failover vm-fileserver (2-5 min downtime)

- Failover vm-pdc LAST (if approved) (5-10 min downtime)

- Verify everything works

- Update DNS if needed

## Phase 5: Cleanup

- Monitor for 1-2 weeks

- Delete old VMs in West US (after confirmation)

# TIMELINE ESTIMATE

| Phase | Duration |
| --- | --- |
| Preparation | 1-2 days |
| Replication | 2-3 days |
| Testing | 1 day |
| Failover | 1-2 hours (during maintenance window) |
| TOTAL | 5-7 business days |

# RISKS

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Domain Controller failure | HIGH | Ensure backup DC exists first |
| IP address changes | MEDIUM | Plan DNS updates |
| Data loss | LOW | Take snapshots before migration |
| Extended downtime | MEDIUM | Do test failover first |

# MY RECOMMENDATION

- Move PyxSftp and vm-fileserver first (low risk)

- Move vm-pdc only AFTER confirming backup DC exists

- Use Azure Site Recovery for minimal downtime

- Schedule a maintenance window for the failover

- Do a test failover before production failover

# NEXT STEPS

Once you provide the answers above, I will:

- Create the full migration script

- Set up Azure Site Recovery

- Start replication

- Schedule the failover with you

Please review and let me know your answers to the questions above.

Thanks,

Syed

Date: 1/7/2026